## 2022-23
SM Projects for Funding Year 2022-23 (State Supported and Local Only)
District Code | District Name | Project | Scope | State Funds | Local Funds | Total Funds | Expended | Remaining | Type | Project Manager | Problem Years | Adverse Effect | Corrective Method | Campus | Building
050 | MiraCosta Community College District | Repaint SAN 700 | Repaint SAN 700 | 20000 | 0 | 20000 | 20000 | 0 | Other | Tracy Gibson | 2-5 yrs. | Inconvenience | Replace s/comparable Unit | San Elijo Center | 700 - B700 - Maintenance
050 | MiraCosta Community College District | OCN 2100 Wood HVAC/Ducting Replacment (bid and confirmed) | OCN 2100 Wood HVAC/Ducting Replacment (bid and confirmed) | 216470 | 0 | 216470 | 216470 | 0 | Mechanical | Tracy Gibson | 2-5 yrs. | Disruption of Program(s) | Replace s/comparable Unit | MiraCosta College (Oceanside Campus) | 2100 - B2100 Art
050 | MiraCosta Community College District | OCN 2000 Lighting Infrastructure Replacement | OCN 2000 Theater Lighting Infrastructure Replacement - OCN 2000 Theater Lighting Theater B2000 Lighting Renovation to replace Electro Controls Dimmer Rack, Distribution Rack and associated wiring. | 220580 | 0 | 220580 | 220580 | 0 | Other | Megan Evanary | 2-5 yrs. | Safety Hazard | Replace s/comparable Unit | MiraCosta College (Oceanside Campus) | 2000 - B2000 Theatre
050 | MiraCosta Community College District | OCN Replace Broken Concrete Dump Yard Access Ramp by 4C | OCN Replace Broken Concrete Dump Yard Access Ramp by 4C | 14400 | 0 | 14400 | 14400 | 0 | Other | Wendell Fullwood | 2-5 yrs. | Safety Hazard | Repair/Refinish Existing | MiraCosta College (Oceanside Campus)
050 | MiraCosta Community College District | OCN Replace Curb cut out ADA by 4C | OCN Replace Curb cut out ADA by 4C | 18400 | 0 | 18400 | 18400 | 0 | Other | Wendell Fullwood | 1-2 yrs. | Code Violation | Repair/Refinish Existing | MiraCosta College (Oceanside Campus)
050 | MiraCosta Community College District | OCN Stadium Replace Damaged external sidewalk concrete pad | OCN Stadium Replace Damaged external sidewalk concrete pad | 21000 | 0 | 21000 | 21000 | 0 | Other | Wendell Fullwood | 2-5 yrs. | Safety Hazard | Repair/Refinish Existing | MiraCosta College (Oceanside Campus)
050 | MiraCosta Community College District | Energy Efficiency CLC/SAN Photovoltaic Energy Project | Energy Efficiency CLC/SAN Photovoltaic Energy Project | 1871273 | 0 | 1871273 | 0 | 1871273 | Other | Louis McGowan | 1-2 yrs. | Inconvenience | Other | San Elijo Center, Community Learning Center
050 | MiraCosta Community College District | Replace Fire Main Valves Pavilion Lawn | Replace Fire Main Valves Pavilion Lawn | 31930 | 0 | 31930 | 31330 | 600 | Utility | Wendell Fullwood | 2-5 yrs. | Safety Hazard | Replace s/comparable Unit | MiraCosta College (Oceanside Campus)
050 | MiraCosta Community College District | SAN 800 Renovation lights, ceiling tile, carpet, paint interior and exterior, restroom ADA, door hardware access control | SAN 800 Renovation lights, ceiling tile, carpet, paint interior and exterior, restroom ADA, door hardware access control | 705182 | 98310 | 803492 | 803492 | 0 | Other | Tracy Gibson | 2-5 yrs. | Disruption of Program(s) | Other | San Elijo Center | 800 - B800 - Administration
050 | MiraCosta Community College District | Exterior Painting , Exterior building Repairs SAN 800 | Exterior Painting , Exterior building Repairs SAN 800 | 24000 | 0 | 24000 | 24000 | 0 | Exterior | Tracy Gibson | 2-5 yrs. | Greater Future Damage/Costs | Repair/Refinish Existing | San Elijo Center | 800 - B800 - Administration
050 | MiraCosta Community College District | 4800 Boiler OCN Campus | Replace Boiler B4800 | 57947 | 0 | 57947 | 57947 | 0 | Mechanical | Tracy Gibson | 6 mo. - 1yrs. | Disruption of Program(s) | Replace s/comparable Unit | MiraCosta College (Oceanside Campus) | 4800 - B4800 Business
050 | MiraCosta Community College District | Facilities Building Shops Lighting Replacement of T-8"s with LED's | Facilities Building Shops Lighting Replacement of T-8"s with LED's | 40500 | 0 | 40500 | 40500 | 0 | Utility | Tracy Gibson | 1-2 yrs. | Safety Hazard | Replace s/comparable Unit | MiraCosta College (Oceanside Campus) | 4200 - B4200 Facilities
|  |  |  | 3241682 | 98310 | 3339992 | 1468119 | 1871873

## 2023-24
SM Projects for Funding Year 2023-24 (State Supported and Local Only)
District Code | District Name | Project | Scope | State Funds | Local Funds | Total Funds | Expended | Remaining | Type | Project Manager | Problem Years | Adverse Effect | Corrective Method | Campus | Building
050 | MiraCosta Community College District | OCN 3400 Rollup door unit replacement | OCN 3400 Rollup door unit replacement | 0 | 30000 | 30000 | 0 | 30000 | Other | Wendell Fullwood | 1-2 yrs. | Safety Hazard | Replace s/comparable Unit | MiraCosta College (Oceanside Campus) | 3400 - B3400 Student Center
050 | MiraCosta Community College District | OCN Replace Pressure Regulator for Stadium | OCN Replace Pressure Regulator for Athletic Field | 0 | 17000 | 17000 | 0 | 17000 | Utility | Wendell Fullwood | 2-5 yrs. | Disruption of Program(s) | Replace s/comparable Unit | MiraCosta College (Oceanside Campus)
050 | MiraCosta Community College District | OCN 7000 Hort Replace Mini split Units | OCN 7000 Hort Replace Mini split Units | 0 | 17500 | 17500 | 0 | 17500 | Mechanical | Tracy Gibson | 1-2 yrs. | Disruption of Program(s) | Replace s/comparable Unit | MiraCosta College (Oceanside Campus) | 7000 - B7000 Horticulture
050 | MiraCosta Community College District | Reclaim Water Project Conversion - Olivenhain MWD | Reclaim Water Project Conversion - Olivenhain MWD | 0 | 300000 | 300000 | 0 | 300000 | Other | Wendell Fullwood | 6 mo. - 1yrs. | Code Violation | Upgrade | San Elijo Center
050 | MiraCosta Community College District | Roofing Project - Multiple Buildings | Replace Roofing on T110, B6100 and B8000. | 0 | 282000 | 282000 | 0 | 282000 | Roof | Mike Turner | 2-5 yrs. | Greater Future Damage/Costs | Replace s/comparable Unit | MiraCosta College (Oceanside Campus) | 110 - T110 Offices, 6100 - B6100 Rcvg/Warehouse, 8000 - B8000 Child Dev Center
050 | MiraCosta Community College District | B3600 ADA Door Operator | Replace ADA Door Operator | 0 | 20000 | 20000 | 0 | 20000 | Exterior | Mike Turner | 1-2 yrs. | Code Violation | Replace s/comparable Unit | MiraCosta College (Oceanside Campus) | 3600 - B3600A Classrooms/Office
050 | MiraCosta Community College District | Fire Alarm Replacement/Replace Damaged Drywall SAN 700 | Fire Alarm Replacement/Replace Damaged Drywall SAN 700 | 0 | 90000 | 90000 | 0 | 90000 | Other | Tracy Gibson | 1-2 yrs. | Code Violation | Replace s/comparable Unit | San Elijo Center | 700 - B700 - Maintenance
|  |  |  | 0 | 756500 | 756500 | 0 | 756500

## 2024-25
SM Projects for Funding Year 2024-25 (State Supported and Local Only)
District Code | District Name | Project | Scope | State Funds | Local Funds | Total Funds | Expended | Remaining | Type | Project Manager | Problem Years | Adverse Effect | Corrective Method | Campus | Building
050 | MiraCosta Community College District | Roof Replacement Multiple Buildings (OCN 4400, 4600, 4700) | Roof Replacement Multiple Buildings (OCN 4600, 4700) | 0 | 318500 | 318500 | 0 | 318500 | Roof | Tracy Gibson | 2-5 yrs. | Disruption of Program(s) | Replace s/comparable Unit | MiraCosta College (Oceanside Campus) | 4600 - B4600 Classrooms/Ass. Fa, 4700 - B4700 Office of Instr
050 | MiraCosta Community College District | Campus Police Building Storm Drain Sump Replacement Connection | Campus Police Building Storm Drain Sump Replacement Connection | 0 | 125000 | 125000 | 0 | 125000 | Utility | Wendell Fullwood | 2-5 yrs. | Code Violation | Replace s/comparable Unit | MiraCosta College (Oceanside Campus)
050 | MiraCosta Community College District | Corrugated Storm Drain Replacement at Theater from 2700 across to Lot 2A | Corrugated Storm Drain Replacement at Theater from 2700 across to Lot 2A | 0 | 150000 | 150000 | 0 | 150000 | Utility | Wendell Fullwood | 2-5 yrs. | Code Violation | Replace s/comparable Unit | MiraCosta College (Oceanside Campus)
050 | MiraCosta Community College District | OCN Paint Fire Hydrants From Red to Yellow | District Wide Paint Fire Hydrants From Red to Yellow | 0 | 25000 | 25000 | 0 | 25000 | Other | Wendell Fullwood | 6 mo. - 1yrs. | Code Violation | Repair/Refinish Existing | MiraCosta College (Oceanside Campus), San Elijo Center, Community Learning Center
050 | MiraCosta Community College District | OCN 7000 Hort Domestic Water Leak Break | OCN 7000 Hort Domestic Water Leak Break | 0 | 15380 | 15380 | 0 | 15380 | Utility | Tracy Gibson | 0 yrs. | Disruption of Program(s) | Repair/Refinish Existing | MiraCosta College (Oceanside Campus) | 7000 - B7000 Horticulture
050 | MiraCosta Community College District | OCN Campus Wide Replace Outdated/broken Intrusion/Fire Notification System | OCN Campus Wide Replace Outdated/broken Intrusion/Fire Notification System | 0 | 100000 | 100000 | 0 | 100000 | Other | Tracy Gibson | 2-5 yrs. | Safety Hazard | Replace s/comparable Unit | MiraCosta College (Oceanside Campus)
050 | MiraCosta Community College District | OCN Main Fire Pump Replacement Phase 1 | Replace OCN Main Fire Pumps Phase 2 | 0 | 133000 | 133000 | 0 | 133000 | Mechanical | Wendell Fullwood | 1-2 yrs. | Potential/Future Damage/Cost | Replace s/comparable Unit | MiraCosta College (Oceanside Campus) | 1 - B1 - Pump House
|  |  |  | 0 | 866880 | 866880 | 0 | 866880

## 2025-26
SM Projects for Funding Year 2025-26 (State Supported and Local Only)
District Code | District Name | Project | Scope | State Funds | Local Funds | Total Funds | Expended | Remaining | Type | Project Manager | Problem Years | Adverse Effect | Corrective Method | Campus | Building
050 | MiraCosta Community College District | OCN 3400 AHU Replacement | OCN 3400 AHU Replacement | 0 | 231000 | 231000 | 0 | 231000 | Mechanical | Tracy Gibson | 2-5 yrs. | Disruption of Program(s) | Replace s/comparable Unit | MiraCosta College (Oceanside Campus) | 3400 - B3400 Student Center
050 | MiraCosta Community College District | OCN 4400 AHU - 3 Unites Replacement | OCN 4400 AHU - 3 Unites Replacement | 0 | 135096 | 135096 | 0 | 135096 | Exterior | Tracy Gibson | 2-5 yrs. | Greater Future Damage/Costs | Replace s/comparable Unit | MiraCosta College (Oceanside Campus) | 4400 - B4400 - Allied Health
050 | MiraCosta Community College District | Multiple Chiller Replacement OCN 2000/2200 | OCN 2000 Theater Chiller Replacement | 0 | 255134 | 255134 | 0 | 255134 | Mechanical | Tracy Gibson | 2-5 yrs. | Disruption of Program(s) | Replace s/comparable Unit | MiraCosta College (Oceanside Campus) | 2200 - B2200 Creative Arts Repl, 2000 - B2000 Theatre
050 | MiraCosta Community College District | OCN 4800 hhw boiler and pumps | OCN 4800 hhw boiler and pumps | 0 | 46600 | 46600 | 0 | 46600 | Mechanical | Tracy Gibson | 2-5 yrs. | Disruption of Program(s) | Replace s/comparable Unit | MiraCosta College (Oceanside Campus) | 4800 - B4800 Business
050 | MiraCosta Community College District | OCN Barnard Drive Paving and Striping | OCN Barnard Drive Paving and Striping | 0 | 183400 | 183400 | 0 | 183400 | Utility | Wendell Fullwood | 2-5 yrs. | Safety Hazard | Repair/Refinish Existing
050 | MiraCosta Community College District | Replace OCN damaged safety hazard stamped concrete/sidewalks leading from the campus into a parking lot | Replace OCN damaged safety hazard stamped concrete/sidewalks leading from the campus into a parking lot | 0 | 14200 | 14200 | 0 | 14200 | Other | Wendell Fullwood | 2-5 yrs. | Safety Hazard | Repair/Refinish Existing | MiraCosta College (Oceanside Campus)
|  |  |  | 0 | 865430 | 865430 | 0 | 865430

## 2026-27
SM Projects for Funding Year 2026-27 (State Supported and Local Only)
District Code | District Name | Project | Scope | State Funds | Local Funds | Total Funds | Expended | Remaining | Type | Project Manager | Problem Years | Adverse Effect | Corrective Method | Campus | Building
050 | MiraCosta Community College District | OCN Replace sidewalk concrete landing and slope repair by 3E | OCN Replace sidewalk concrete landing and slope repair by 3E | 0 | 13200 | 13200 | 0 | 13200 | Other | Wendell Fullwood | 2-5 yrs. | Safety Hazard | Repair/Refinish Existing | MiraCosta College (Oceanside Campus)
050 | MiraCosta Community College District | Multiple Roof Replacement Project | Multiple Roof Project 310,2200,2300,300,4000BAuto | 0 | 644000 | 644000 | 0 | 644000 | Roof | Mike Turner | 2-5 yrs. | Disruption of Program(s) | Replace s/comparable Unit | MiraCosta College (Oceanside Campus) | 310 - T310 Offices, 2200 - B2200 Creative Arts Repl, 2300 - B2300 Art/Music, 300 - T300 Office/Classroom, 4001 - B4000 Auto Technology B
050 | MiraCosta Community College District | Fire Main Replacement from Hort to Automotove across to B4000 | Fire Main Replacement from Hort to Automotove across to B4000 | 0 | 165000 | 13200 | 0 | 13200 | Utility | Wendell Fullwood | 2-5 yrs. | Campus/Facility Closure | Replace s/comparable Unit | MiraCosta College (Oceanside Campus)
|  |  |  | 0 | 822200 | 670400 | 0 | 670400